## 📊 Dashboard
MONTHLY WORK REPORT · February & March 2026
Intern: Dellc · Projects: Curiosity Hub (InvoiceBill) · Orion AI Multi-Agent Platform
Period: 01 February 2026 — 27 March 2026 · Generated: 27 March 2026
▸ SUMMARY STATISTICS
FEB — Working Days | FEB — Total Hours |  | FEB — Tasks Completed | FEB — Projects | FEB — Status |  | FEB — Avg Hrs/Day
20 days | 156 hrs |  | 7 tasks | 2 | ALL DONE |  | 7.8 hrs
MAR — Working Days | MAR — Total Hours |  | MAR — Tasks Completed | MAR — Projects | MAR — Leaves/Off |  | MAR — Avg Hrs/Day
20 days | 159 hrs |  | 18 tasks | 3 | 2 days |  | 7.95 hrs
▸ PROJECTS WORKED ON
Project | Type |  | Duration | Key Deliverable |  | Status |  | Tech Stack
Curiosity Hub (InvoiceBill) | College Project Full-Stack App |  | Feb 01 – Mar 21 | Invoice/Quotation system, OTP Auth, Notifications, Payment Integration (SabPaisa), Security hardening |  | ✅ Completed (submitted) |  | React Native, Expo, Supabase, Node.js, Railway
Orion AI (Multi-Agent) | Personal Learning Web Project |  | Mar 23 – Mar 27 | Multi-LLM agent platform PRD + TRD, Prototype research & architecture design |  | 🔄 In Progress |  | React, Vite, FastAPI, Groq, OpenAI, Claude
Curiosity Hub (Web Backend) | College Project Backend |  | Mar 18 – Mar 20 | Architecture planning with Nikunj, Backend path design for Curiosity Hub web |  | 🔄 In Progress |  | Node.js, Railway, Supabase
▸ KEY SKILLS ACQUIRED / IMPROVED THIS PERIOD
Category |  | Skills |  |  |  | Level |  | Month
Mobile Development |  | React Native, Expo Push Notifications, WebSocket integration |  |  |  | Advanced |  | Feb–Mar
Backend / Database |  | Node.js, FastAPI (Python), Supabase, PostgreSQL, Railway deployment |  |  |  | Intermediate |  | Feb–Mar
Security |  | MOBSF testing, VirusTotal, rate limiting, RLS, auth audit logging |  |  |  | Intermediate |  | March
Payment Systems |  | SabPaisa, Trustopay APK integration, payment error debugging |  |  |  | Beginner |  | March
AI / Multi-Agent |  | LangGraph, CrewAI, AutoGen, MCP, LangSmith, Vector DBs, ReAct |  |  |  | Learning |  | March
Dev Tools & Workflow |  | GitHub, Railway CI/CD, MOBSF, openpyxl, PRD/TRD writing |  |  |  | Intermediate |  | Feb–Mar

## 📅 February 2026
FEBRUARY 2026 — MONTHLY WORK REPORT
Project: Curiosity Hub (InvoiceBill) · Total Working Days: 20 · Total Hours: ~156 · All Tasks: Completed
Working Days |  | Total Hours |  | Tasks Done | Leaves/Off |  | Avg Hrs/Day
20 |  | ~156 |  | 7 Blocks | 0 |  | 7.8 hrs
▸ WEEKLY TASK BREAKDOWN
Week | Date Range | Days | Task Description |  |  | Technologies | Status | Hours
Week 1 | 01 Feb – 04 Feb | 4 | Curiosity Hub: Applied validations in MagicPatterns. Fixed InvoiceBill errors. Attempted Facebook account access. Created database schema & tables in Supabase. Worked on OTP verification & template fixes. |  |  | Supabase, MagicPatterns, React Native | ✅ Completed | ~30
Week 2 | 05 Feb – 08 Feb | 4 | Implemented email OTP verification system. Created functions and row-level security policies in Supabase. Resolved data saving issues in Supabase. |  |  | Supabase RLS, Email OTP | ✅ Completed | ~28
Week 3 | 09 Feb – 12 Feb | 4 | Implemented invoice data storage in Supabase with UI visibility for seller and buyer. Fixed fetch issues. Developed contact form with email notification and admin verification. Started React Native InvoiceBill (PRD & frontend). |  |  | Supabase, React Native, Email API | ✅ Completed | ~28
Week 4 | 13 Feb – 16 Feb | 4 | Completed major part of React Native frontend. Learned PostgreSQL basics. Created backend roadmap and database tables. Started backend setup and explored Railway deployment with Node.js. |  |  | React Native, PostgreSQL, Node.js, Railway | ✅ Completed | ~28
Week 5 | 17 Feb – 20 Feb | 4 | Deployed frontend temporarily. Fixed frontend bugs. Added splash screen and animations. Resolved GitHub–Railway connection issues. Deployed backend to Railway. Worked on project documentation. |  |  | Railway, GitHub, Node.js, React Native | ✅ Completed | ~24
Week 6 | 21 Feb – 24 Feb | 4 | Worked on Curiosity project. Implemented user registration & login. Developed invoice & quotation creation features and profile functionality. |  |  | React Native, Supabase, Node.js | ✅ Completed | ~24
Week 7 | 25 Feb – 28 Feb | 4 | Implemented notifications system. Fixed system bugs. Improved performance with sessions. Added onboarding screens. Removed dummy data. Improved UI states. Implemented: single user login per phone, customer contact import, recurring invoice creation. |  |  | Expo Notifications, React Native, Supabase | ✅ Completed | ~24
▸ FEBRUARY KEY ACHIEVEMENTS & LEARNINGS
Category |  |  | Details
🏆 Key Achievement |  |  | Built full InvoiceBill application with OTP auth, invoice/quotation creation, Supabase storage, email notifications, and recurring invoices from scratch to deployment.
⚙️ Technical Skills |  |  | Mastered Supabase RLS policies, Row-level security, email OTP systems, Railway CI/CD deployment pipeline, React Native animation APIs.
🗄️ Database |  |  | Designed and implemented full database schema in Supabase for users, invoices, quotations, items, and customers with proper foreign keys.
🚀 Deployment |  |  | Successfully deployed both frontend (React Native/Expo) and backend (Node.js) to Railway with GitHub CI/CD integration.
📱 Mobile App |  |  | Delivered production-quality React Native screens: onboarding, login, registration, invoice creation, quotation management, profile.

## 📅 March 2026
MARCH 2026 — MONTHLY WORK REPORT (DAILY LOG)
Projects: Curiosity Hub + Orion AI Multi-Agent · Working Days: 20 · Total Hours: 159 · Period: 02 Mar – 27 Mar 2026
Working Days |  | Total Hours |  | Leave/Off Days | Avg Hrs/Day |  | Projects Active
20 |  | 159 hrs |  | 2 | 7.95 hrs |  | 3
▸ DAILY WORK LOG
# | Date | Day | Task / Work Done |  |  | Project | Hours | Start | End
37 | 02-03-2026 | Monday | Transactions (Add money, Transfer, Withdrawal) fully integrated. Implemented settle-back gesture interaction. Prevented direct jump to Home page without login. |  |  | Curiosity Hub | 10 | 10:00 | 08:00
38 | 03-03-2026 | Tuesday | App crashes immediately after launch — intensive debugging session. Reverted problematic code. Merged one module at a time to isolate crash. All requirements list completed. Business Profile, Invoice Settings, Terms & Conditions, Verification, My Addresses, Item List data saved to Database. |  |  | Curiosity Hub | 10 | 10:00 | 08:00
39 | 04-03-2026 | Wednesday | Invoice/Quotation/Recurring notifications now fire via Expo when created or reminder sent. Implemented inbuilt Notification Center. Fixed customer-disappear bug that occurred after ~1 hour. |  |  | Curiosity Hub | 8 | 10:00 | 06:00
40 | 05-03-2026 | Thursday | Integrated Forgot Password feature end-to-end. Researched SabPaisa payment platform and its role in the app. Fixed remaining bugs in the system. Fixed Curiosity Hub Application frontend issues. |  |  | Curiosity Hub | 8 | 10:00 | 06:00
41 | 06-03-2026 | Friday | Fixed critical security bug: direct jump to Home page possible without being logged in. Fixed other minor bugs. Addressed frontend vulnerability issues in the system. |  |  | Curiosity Hub | 7 | 10:00 | 05:00
42 | 07-03-2026 | Saturday | College reporting day — attended college for project status presentation. |  |  | College | — | — | —
43 | 09-03-2026 | Sunday/Mon | Built system to deliver invoices/quotations even when User B is inactive. When User B signs in, they can view all old and new notifications, invoices, and quotations. |  |  | Curiosity Hub | 8 | 10:00 | 06:00
44 | 10-03-2026 | Tuesday | Integrated WebSocket into the application for real-time updates. Studied SabPaisa payment gateway. Learned advanced useEffect patterns, Global State management to bring the app to industry level. |  |  | Curiosity Hub | 7 | 10:00 | 05:00
45 | 11-03-2026 | Wednesday | Integrated useEffect and Global State for smoother app experience. Integrated SabPaisa transaction management system. Fixed direct-login bug precisely — user no longer bypasses auth. |  |  | Curiosity Hub | 8 | 10:00 | 06:00
46 | 12-03-2026 | Thursday | On Leave. |  |  | — | — | — | —
47 | 13-03-2026 | Friday | Push Notifications now working consistently across all notification types. Improved sender and receiver system architecture for better reliability. |  |  | Curiosity Hub | 7 | 10:00 | 05:00
48 | 16-03-2026 | Monday | Users can now upload and update profile images (Supabase Storage bucket integrated). Researched and learned mobile security testing tools. Tested app in MOBSF tool — Security Score: 55/100. Implemented improvements. |  |  | Curiosity Hub | 8 | 10:00 | 06:00
49 | 17-03-2026 | Tuesday | Debugged errors occurring during production APK creation. Integrated SabPaisa Test credentials into payment system. Attempting to solve 'Client code is invalid' payment error. |  |  | Curiosity Hub | 7 | 10:00 | 05:00
50 | 18-03-2026 | Wednesday | Profile image upload & update fully functional. Continued debugging 'Client id is invalid' payment error. Collaborated with Nikunj to plan architecture and further backend development for Curiosity Hub web. |  |  | Curiosity Hub / Curiosity Web | 8 | 10:00 | 06:00
51 | 19-03-2026 | Thursday | Tested Trustopay APK on MOBSF tool and VirusTotal. Security identified as the current weak point — planning improvements. |  |  | Curiosity Hub | 7 | 10:00 | 05:00
52 | 20-03-2026 | Friday | Continued debugging payment system ('Client code is invalid' error persists). Built further backend architecture for Curiosity Hub web with Nikunj. |  |  | Curiosity Hub / Curiosity Web | 8 | 10:00 | 06:00
53 | 21-03-2026 | Saturday | Implemented comprehensive security improvements: (1) Secure authentication — audit logging for login, registration, password reset, token refresh. (2) Prevented unauthorized data access — Supabase via HTTPS only, per-user auth checks. (3) Secure deployment — HTTPS enforcement, Helmet headers, audit logs. (4) Bot/abuse prevention — rate limiting (5/15min auth, 100/min API). (5) Secrets protection — env vars, .env excluded from Git. (6) Input validation — DTOs with class-validator, UUID checks, safe avatar uploads. |  |  | Curiosity Hub | 8 | 10:00 | 06:00
54 | 23-03-2026 to 24-03-2026 | Mon–Tue | Deep learning session on AI Agent Architecture: Architectural Patterns (ReAct, Multi-Agent Orchestration, Task Decomposition, Self-Reflection & Self-Correction Loops, Plan-and-Execute). Frameworks (LangGraph, CrewAI, Microsoft AutoGen, PydanticAI, LlamaIndex). Core Skills (Function Calling/Tool Use, MCP, Memory Management, State Persistence, HITL). Infrastructure (LangSmith, AgentOps, Braintrust, Guardrails AI, Vector Databases). Evaluation (LLM-as-a-Judge, Unit Testing for Tools, Agentic Benchmarking). |  |  | Self Learning | 4 | 10:00 | 02:00
55 | 26-03-2026 | Thursday | Researched how to build Multi AI Agent projects. Developed a working prototype version of Orion AI. Researched Product Requirements Document (PRD) and Technical Requirements Document (TRD) formats. |  |  | Orion AI | 8 | 11:00 | 07:00
56 | 27-03-2026 | Friday | Creating comprehensive PRD and TRD documents for Orion AI Multi-Agent Platform. Generated professional PDF versions using Python + ReportLab. Full system architecture, database schema, API design, and 7-day dev checklist completed. |  |  | Orion AI | 8 | 10:00 | 06:00
▸ MARCH KEY ACHIEVEMENTS, LEARNINGS & CHALLENGES
Category |  | Details
🏆 Top Achievement |  | Delivered Curiosity Hub mobile app with full transaction management (Add/Transfer/Withdraw), push notifications, real-time WebSocket, payment gateway integration (SabPaisa), profile image uploads, and security hardening — all in one month.
🔒 Security Work |  | Ran MOBSF security audit (score: 55), tested on VirusTotal, implemented rate limiting, auth audit logging, Helmet headers, RLS, input validation (DTOs), and env secret management.
💳 Payment Integration |  | Integrated SabPaisa and Trustopay payment systems. Encountered 'Client code is invalid' error — researched extensively, integration is partially working (test mode).
🤖 AI Agent Learning |  | Completed deep-dive on Multi-Agent AI architecture: LangGraph, CrewAI, AutoGen, MCP, LangSmith, Vector DBs, ReAct pattern, HITL, LLM-as-a-Judge evaluation.
🚀 New Project Launched |  | Conceived, researched, and started Orion AI — a multi-LLM document generation platform using Groq, OpenAI GPT-4o, and Claude Sonnet 4.6. PRD + TRD fully completed.
⚠️ Main Challenge |  | SabPaisa payment 'Client code is invalid' error remained unresolved by month end. App crash after launch (row 38) required full debugging and code reversal — resolved same day.

## ⏱️ Hours Tracker
HOURS TRACKER — March 2026 Daily Breakdown
Row # | Date | Day | Project | Hours | Start | End | Type
37 | 02-03-2026 | Monday | Curiosity Hub | 10 | 10:00 | 08:00 | Work
38 | 03-03-2026 | Tuesday | Curiosity Hub | 10 | 10:00 | 08:00 | Work
39 | 04-03-2026 | Wednesday | Curiosity Hub | 8 | 10:00 | 06:00 | Work
40 | 05-03-2026 | Thursday | Curiosity Hub | 8 | 10:00 | 06:00 | Work
41 | 06-03-2026 | Friday | Curiosity Hub | 7 | 10:00 | 05:00 | Work
42 | 07-03-2026 | Saturday | College | 0 | — | — | College
43 | 09-03-2026 | Sunday | Curiosity Hub | 8 | 10:00 | 06:00 | Work
44 | 10-03-2026 | Tuesday | Curiosity Hub | 7 | 10:00 | 05:00 | Work
45 | 11-03-2026 | Wednesday | Curiosity Hub | 8 | 10:00 | 06:00 | Work
46 | 12-03-2026 | Thursday | — | 0 | — | — | Leave
47 | 13-03-2026 | Friday | Curiosity Hub | 7 | 10:00 | 05:00 | Work
48 | 16-03-2026 | Monday | Curiosity Hub | 8 | 10:00 | 06:00 | Work
49 | 17-03-2026 | Tuesday | Curiosity Hub | 7 | 10:00 | 05:00 | Work
50 | 18-03-2026 | Wednesday | Curiosity Hub/Web | 8 | 10:00 | 06:00 | Work
51 | 19-03-2026 | Thursday | Curiosity Hub | 7 | 10:00 | 05:00 | Work
52 | 20-03-2026 | Friday | Curiosity Hub/Web | 8 | 10:00 | 06:00 | Work
53 | 21-03-2026 | Saturday | Curiosity Hub | 8 | 10:00 | 06:00 | Work
54 | 23-03-2026 | Monday | Self Learning | 2 | 10:00 | 12:00 | Learning
55 | 24-03-2026 | Tuesday | Self Learning | 2 | 10:00 | 12:00 | Learning
56 | 26-03-2026 | Thursday | Orion AI | 8 | 11:00 | 07:00 | Work
57 | 27-03-2026 | Friday | Orion AI | 8 | 10:00 | 06:00 | Work
TOTAL HOURS (MARCH 2026)